## Sheet1
Work Flow For Process Parameter Project
Sr.No | Task | Implementation Time | Remark
1 | Create Data Structure | 2 days
2 | Confirmation of Data Structure | 2 days
3 | Create Web Application for Master Entry | 1 week | 15 forms are there
4 | Design UI for supervisor App(android app for tab) on paper | 2-3 days
5 | Approval of design from directors | 2 days
6 | Design UI for supervisor App(android app for tab) | 2 week
7 | Binding of App with database | 2 week
8 | Testing of Web application | 1 week
9 | Testing of Supervisor App | 1 week
* | Implemintation time as per manpower availability for Web & Mobile app development